Early Learning Coalition of North Florida

ECS Sub-recipient Contract Monitoring Schedule

2015/2016

(Created 05/21/15)

Deadlines:

| Qtr/Period to be Monitored (new subject areas may include previous quarters) | Schedule Pre-Monitoring Meeting and begin monitoring docs: (have all mon. docs done & sent to Contractor 2-3 days before the pre-mon. meeting beginning target date) | Pre-Monitoring Meeting Target Dates (at least 2 weeks before notification letter, and before sampling) | Request to run EFS Reports and upload to Share Point (for sampling) sent to ECS (Leighton/Alicia Baltzell) (give at least one week’s notice) | Sampling – begin by: (at least 2 weeks before notification letter due) (calculations, request/run EFS reports, sample, create spreadsheet and Fiscal samples sent from Coalition Fiscal Manager | Notification Letter– Due date (8 weeks’ notice) (with Request for Documents, schedule, tools, fiscal samples sent, and sample spreadsheets uploaded to SharePoint – with full names. | ELC Finance Mgr. to send ECS all fiscal samples (by 9:00 am, five business days before on-site monitoring) | Monitoring Dates (2-3 weeks scheduled, but if finished before the 2 weeks are over, will adjust exit interview date/time and all subsequent due dates) | Draft Report Due (1 week after monitoring completed) | Contractor Response to Draft Report (including tool comments and supporting documents) (1 week after draft report) | Final Report Due (1 week after contractor response to draft) | Contractor Response to Final Report and CAP Due (1 week from final report) | Coalition CAP Acceptance / Denial letter (with terms) (1 week from response) | Receipt of all CAP items – deadline (4 weeks from acceptance letter) | Close-out Letter (within 1 week of CAP items received) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1Q (July – Sept 2015) | Late May | 06/29/15 – 07/10/15 | 07/24/15 (July reports) | 08/18/15 | 08/31/15 | 10/19/15 | October 26 – November 6, 2015 | 11/16/15 (holiday) | 11/23/15 | 12/01/15 (holidays) | 12/08/15 | 12/15/15 | 01/12/16 | 01/20/16 |
| 2Q (Oct – Dec 2015) | Early September | 10/05/15 – 10/16/15 | 10/23/15 (October reports) | 11/12/15 | 11/30/15 | 01/15/16 | January 25 – February 5, 2016 | 02/12/16 | 02/22/16 (holiday) | 02/26/16 | 03/04/16 | 03/11/16 | 04/08/16 | 04/15/16 |
| 3Q (Jan – Mar 2016) | Early December | 01/04/16 – 01/15/16 | 01/22/16 (January reports) | 02/16/16 | 02/29/16 | 04/18/16 | April 25 – May 6, 2016 | 05/13/16 | 05/20/16 | 05/27/16 | 06/06/16 (holiday) | 06/13/16 | 07/11/16 | 07/18/16 |
| 4Q (Apr-June 2016) | Early March | 04/04/16 – 04/15/16 | 04/22/16 (April reports) | 05/16/16 | 05/27/16 | 07/18/16 | July 25 – August 5, 2016 | 08/12/16 | 08/19/16 | 08/26/16 | 09/02/16 | 09/12/16 (holiday) | 10/10/16 | 10/17/16 |
| 4Q (June 2016) |  | The Coalition’s Fiscal Manager will set dates for June’s non-direct cost review and 4th Qtr Contract Monitoring Tool review. This will be a separate monitoring, as the Coalition will not receive the June non-direct costs invoice until August 15. |  |  |  |  |  |  |

- (areas of review and dates are subject to change)

Early Learning Coalition of North Florida

Sub-recipient Contract Monitoring Schedule

2015/2016

(Created 05/21/15)

Subject Areas to be Monitored:

| Qtr | Contract/Subject Areas to be Monitored | Monitoring Dates |
| --- | --- | --- |
| 1 | Overall: All administrative and programmatic policies/procedures, job descriptions, org chart, etc. review/updates, and data security system updates SR & VPK: Attendance/Payment Validation (1/4 year’s sample - or whatever VPK child (and payment validations) are available for summer programs – then adjust sample numbers for the following 2nd – 4th Quarters to make up for any shortfall), Fiscal-1st Qtr samples (non-direct costs, including staffing allocation), SR: Eligibility and Enrollment (client files) (1/4 year’s sample) VPK: Eligibility and Enrollment (child files) (1/4 year’s sample*) VPK: Provider Services (provider files)(1/4 year’s sample) 2015 Coalition Plan Compliance: None for this quarter OEL Scorecard: TBD Additional: Annual Data and Data Security Systems Review and Annual OEL Attendance/Reimbursement Staff Interviews | October 26 – November 6, 2015 |
| 1-2 | Overall: All administrative and programmatic policies/procedures, job descriptions, org chart, etc. review/updates, and data security system updates SR & VPK: Attendance/Payment Validation (1/4 year’s sample), Fiscal-2nd Qtr samples (non-direct costs, including staffing allocation). SR: Eligibility and Enrollment (client files) (1/4 year’s sample) VPK: Eligibility and Enrollment (child files) (1/4 year’s sample) VPK: Provider Services (provider files)(1/4 year’s sample) 2015 Coalition Plan Compliance: III. C. Inclusion OEL Scorecards: TBD - Additional: None this quarter | January 25 – February 5, 2016 |
| 1-3 | Overall: All administrative and programmatic policies/procedures, job descriptions, org chart, etc. review/updates, and data security system updates SR & VPK: Attendance/Payment Validation (1/4 year’s sample), Fiscal-3rd Qtr samples (non-direct costs, including staffing allocation). SR: Eligibility and Enrollment (client files) (1/4 year’s sample) VPK: Eligibility and Enrollment (child files) (1/4 year’s sample) VPK: Provider Services (provider files)(1/4 year’s sample) 2015 Coalition Plan Compliance: II. B. SPE (Single Point of Entry) OEL Scorecard: TBD Additional: Contract Certifications/Assurances Verification | April 25 – May 6, 2016 |
| 1-4 | Overall: All administrative and programmatic policies/procedures, job descriptions, org chart, etc. review/updates, and data security system updates SR & VPK: Attendance/Payment Validation (1/4 year’s sample), Fiscal-4th Qtr samples (non-direct costs, including staffing allocation), SR: Eligibility and Enrollment (client files) (1/4 year’s sample) VPK: Eligibility and Enrollment (child files) (1/4 year’s sample) VPK: Provider Services (provider files)(1/4 year’s sample) 2015 Coalition Plan Compliance: None this quarter OEL Scorecard: TBD Additional: Fiscal Overview (including review of Cost Allocation Plan, Policies and Procedures, Board minutes, and 4th Quarter Contract Monitoring Tool review for year-end, etc.) | July 25 – August 5, 2016 |